## Sheet1
| Negligable | Marginal | Critical | Catastrophic | R1 | History lookup fails
Certain |  |  |  |  | R2 | Problem adding items to shopping cart
Likely |  |  | R8 | R2 | R3 | Products are lost in shipping
Possible |  | R9 | R1 | R5, R7 | R4 | Project manager slacks off
Unlikely |  | R6 |  | R4, R10 | R5 | Web server fails
Rare |  |  |  | R3 | R6 | User information is not saved for fast checkout
[5 empty] | R7 | Developers cannot setup product database
[5 empty] | R8 | Deadlines are not met
[5 empty] | R9 | Incorrect order status
[5 empty] | R10 | Payment processing manfunctions